## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: |  |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan)
ACTIVITY | PLAN START (Weeks) | PLAN DURATION (Weeks) | ACTUAL START (Weeks) | ACTUAL DURATION (Weeks) | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
EDA | 1 | 5 | 0 | 0 | 25%
Univariate Analysis | 1 | 2 | 0 | 0 | 100%
Missing data Imputation & Outliner treatments | 2 | 1 | 0 | 0 | 35%
Bivariant analysis | 3 | 2 | 0 | 0 | 10%
Clustering | 6 | 4 | 0 | 0 | 85%
Hierarchical Clustering | 6 | 2 | 0 | 0 | 85%
K-means | 8 | 2 | 0 | 0 | 50%
PCA | 10 | 2 | 0 | 0 | 60%
Buffer | 12 | 2 | 0 | 0 | 75%
Time Series Analysis | 14 | 4 | 0 | 0 | 100%
Arima | 14 | 2 | 0 | 0 | 60%
Global Decomposition | 16 | 2 | 0 | 0 | 0%
Consolidation & Report Writing | 18 | 4 | 0 | 0 | 50%
Presentaion | 18 | 3 | 0 | 0 | 0%
Video | 21 | 1 | 0 | 0 | 1%